Smart Parking Platform

Project Management Document

Prepared by: Emilia Menz

Course: CIS 4374

Project repository: CIS Smart Parking Platform

Academic term: Fall 2026

Homework 1: Project Documentation
Homework 2: Work Breakdown Structure and Draft Timeline

Homework 3: Product Backlog and Sprint Planning

# Document Overview

This document presents the semester project plan for a Smart Parking Platform. Homework 1 defines the existing software landscape, project vision, scope, and system use cases. Homework 2 breaks the work into manageable packages and schedules the work across a 12-week semester timeline.

## Contents

Homework 1 Project Documentation	3

1. Research and Existing Software Landscape	3

2. Vision and Scope	4

3. Software Requirements Specification	5

4. References and Project Repository	10

Homework 2 Work Breakdown Structure and Timeline	11

5. Work Breakdown Structure	11

6. Draft Project Timeline	13

7. Gantt Chart	14

8. Milestones and Scheduling Notes	15

## Project Summary

The platform will help drivers locate, reserve, and pay for parking spaces in real time through mobile and web applications. It will also give parking operators tools to manage availability, pricing, reservations, occupancy data, and reports. The project uses separate mobile, web, backend/API, mapping, payment, and quality-assurance work streams.

# Homework 1 Project Documentation

# 1. Research and Existing Software Landscape

Drivers often lose time searching for parking, especially near campuses, business districts, airports, and event venues. This creates frustration, contributes to congestion, and makes it difficult for parking operators to use their spaces efficiently. A smart parking platform can reduce this problem by showing available locations, supporting reservations and digital payments, and providing clear directions before a driver arrives.

Several established products already address parts of this problem. ParkMobile allows drivers to find, reserve, and pay for parking, while its provider tools include dashboards, reservations, payments, management, and insights. SpotHero focuses on comparing parking options and making prepaid reservations for garages, lots, airports, and events. PayByPhone emphasizes digital payment, session extensions, receipts, and parking alerts. These products show that users expect parking technology to be fast, mobile-friendly, and connected to secure payment services.

The proposed Smart Parking Platform would combine driver and operator functions in one coordinated system. Drivers would use a mobile or web application to search an interactive map, view real-time availability, reserve a space, pay digitally, receive alerts, and access receipts. Operators would use an administrative dashboard to update parking information, review reservations, monitor occupancy, manage pricing, and generate reports. The project does not assume that existing parking tools lack these features; instead, it uses the existing market to identify the functions users and operators are likely to expect.

## Competitive Comparison

| Platform | Driver Focus | Notable Functions | Project Lesson |
| --- | --- | --- | --- |
| ParkMobile | Parking now and advance reservations | Search, payment, reservations, provider tools | Combine driver services with operator management. |
| SpotHero | Advance parking reservations | Compare locations and prices, prepaid passes, reservation management | Make search, comparison, and confirmation simple. |
| PayByPhone | Digital parking sessions | Payments, extensions, receipts, and alerts | Support convenient payments and timely notifications. |
| Proposed Platform | Drivers and parking operators | Real-time availability, maps, reservations, payments, dashboards, and analytics | Connect the complete parking process in one system. |

Table 1. Comparison of existing parking platforms and the proposed system.

# 2. Vision and Scope

## 2.1 Project Context

WE ARE Software Corp. is planning the Smart Parking Platform as a semester software-development project. The platform will serve drivers, vehicle owners, parking facility operators, city transportation departments, system administrators, finance personnel, and mobile application users. Development will be divided among mobile, web, backend/API, mapping and location services, payment integration, and quality-assurance teams.

## 2.2 Project Vision

The vision is to create a dependable platform that helps drivers move from searching to parking with fewer delays. The same system will help operators maintain accurate availability information, manage reservations and payments, and understand how their parking facilities are being used. Information should be easy to find, current, and appropriate to each user’s role.

## 2.3 Project Scope

The first release will include user registration and authentication, real-time parking availability, an interactive map, reservations, digital payments, receipts and reservation history, alerts, external navigation integration, an operator dashboard, and occupancy analytics. The web and mobile applications will use shared backend services so information remains consistent across the platform.

The project includes planning, requirements gathering, stakeholder analysis, system design, development, integration, testing, deployment preparation, documentation, and handoff. It assumes an unlimited theoretical development budget but must fit within the semester schedule. The project also depends on third-party mapping and payment services and must consider security, privacy, city ordinances, and applicable laws.

## 2.4 Scope Boundaries

The platform will provide parking information and reservations but will not control traffic signals or city roadway operations.

Payments will be processed through an approved third-party provider rather than storing complete payment-card information in the platform.

Availability accuracy will depend on timely information from parking operators, sensors, gates, or connected facility systems.

The initial release will support the defined semester features; advanced forecasting and dynamic pricing may be considered later.

# 3. Software Requirements Specification

The following use cases describe the primary interactions required for the first release. Together, they cover driver accounts, parking search, reservations, payments, navigation, notifications, operator tools, analytics, and administrative control.

| Use Case 1: Register User Account |  |
| --- | --- |
| Actor | Driver or Parking Operator |
| Goal | Create an authorized platform account. |
| Precondition | The user is not currently registered. |
| Main Flow | The user enters contact information, creates credentials, selects the appropriate account type, and accepts required terms. The system validates the information and creates the account. |
| Postcondition | The account is created and ready for verification or login. |

| Use Case 2: Log In to the Platform |  |
| --- | --- |
| Actor | Registered User |
| Goal | Securely access features permitted for the user’s role. |
| Precondition | The user has an active account. |
| Main Flow | The user enters credentials. The system verifies the information, creates a secure session, and opens the correct driver, operator, or administrator interface. |
| Postcondition | The user is authenticated with role-based access. |

| Use Case 3: Search for Parking |  |
| --- | --- |
| Actor | Driver |
| Goal | Find parking near a destination for a selected date and time. |
| Precondition | The driver is using the mobile or web application. |
| Main Flow | The driver enters a destination, date, and time. The system searches available parking locations and returns matching results. |
| Postcondition | A list of matching parking options is displayed. |

| Use Case 4: View Real-Time Availability on Map |  |
| --- | --- |
| Actor | Driver |
| Goal | See available parking locations visually. |
| Precondition | Parking availability and mapping data are available. |
| Main Flow | The driver opens the interactive map. The system displays parking locations, availability status, distance, and map markers that update when new data is received. |
| Postcondition | The driver can compare available locations on the map. |

| Use Case 5: View Parking Location Details |  |
| --- | --- |
| Actor | Driver |
| Goal | Review a location before selecting it. |
| Precondition | The driver has opened a parking result. |
| Main Flow | The system displays the address, operating hours, price, availability, entrance instructions, restrictions, and accessibility information supplied by the operator. |
| Postcondition | The driver has enough information to select or reject the location. |

| Use Case 6: Reserve a Parking Space |  |
| --- | --- |
| Actor | Driver |
| Goal | Reserve parking for a selected time period. |
| Precondition | The driver is logged in and the location accepts reservations. |
| Main Flow | The driver selects a location and time period. The system verifies availability, temporarily holds capacity, presents the price, and requests confirmation. |
| Postcondition | A pending reservation is created for payment. |

| Use Case 7: Complete Digital Payment |  |
| --- | --- |
| Actor | Driver |
| Goal | Pay securely for a reservation or parking session. |
| Precondition | A payable reservation or session exists. |
| Main Flow | The driver selects a payment method. The platform sends the transaction to the approved payment provider and receives the result. |
| Postcondition | A successful payment confirms the reservation and creates a transaction record. |

| Use Case 8: Navigate to Parking Location |  |
| --- | --- |
| Actor | Driver |
| Goal | Receive directions to the selected parking facility. |
| Precondition | The driver has selected or reserved a location. |
| Main Flow | The driver chooses navigation. The platform transfers the destination to the connected mapping or navigation service and displays available route information. |
| Postcondition | Navigation begins with the correct parking destination. |

| Use Case 9: Modify or Cancel Reservation |  |
| --- | --- |
| Actor | Driver |
| Goal | Change or cancel an eligible reservation. |
| Precondition | The reservation exists and the policy allows changes. |
| Main Flow | The driver opens the reservation, chooses an available action, and confirms the change. The system updates capacity and sends any required payment or refund request. |
| Postcondition | The reservation and availability records are updated. |

| Use Case 10: View Reservation History and Receipt |  |
| --- | --- |
| Actor | Driver |
| Goal | Review previous and upcoming parking activity. |
| Precondition | The driver is logged in and has reservation or payment history. |
| Main Flow | The driver opens account history and selects a record. The system displays dates, location, amount, payment status, and a downloadable receipt. |
| Postcondition | The requested history or receipt is available. |

| Use Case 11: Receive Parking Alerts |  |
| --- | --- |
| Actor | Driver |
| Goal | Receive useful updates about parking activity. |
| Precondition | The driver has enabled notifications or has an active reservation. |
| Main Flow | The system sends confirmations, reminders, expiration warnings, changes, cancellations, or facility instructions through the selected notification channel. |
| Postcondition | The driver receives a timely record of the event. |

| Use Case 12: View Operator Dashboard |  |
| --- | --- |
| Actor | Parking Facility Operator |
| Goal | Monitor current parking operations from one screen. |
| Precondition | The operator is logged in with facility access. |
| Main Flow | The system displays facility status, available capacity, active reservations, recent payments, alerts, and key occupancy measures. |
| Postcondition | The operator receives a current overview of assigned facilities. |

| Use Case 13: Update Parking Inventory and Pricing |  |
| --- | --- |
| Actor | Parking Facility Operator |
| Goal | Keep availability, facility details, and prices accurate. |
| Precondition | The operator has permission to manage the facility. |
| Main Flow | The operator selects a facility or parking area, edits capacity, closures, hours, restrictions, or pricing, and submits the change. The system validates and publishes the update. |
| Postcondition | Driver-facing parking information reflects the approved update. |

| Use Case 14: Generate Occupancy and Revenue Report |  |
| --- | --- |
| Actor | Parking Operator or Finance Personnel |
| Goal | Analyze parking use and financial activity. |
| Precondition | Historical facility, reservation, and payment data are available. |
| Main Flow | The user selects a facility, date range, and report type. The system summarizes occupancy, reservations, cancellations, payments, and revenue and allows export. |
| Postcondition | A report is available for review or export. |

| Use Case 15: Manage Users and Facilities |  |
| --- | --- |
| Actor | System Administrator |
| Goal | Control accounts, roles, permissions, and facility records. |
| Precondition | The administrator is authenticated. |
| Main Flow | The administrator searches for a user or facility, adds or edits approved information, assigns roles, changes access, or deactivates a record. The system records the administrative action. |
| Postcondition | Platform access and facility ownership remain current and controlled. |

# 4. References and Project Repository

## 4.1 References

ParkMobile. “The Smarter Way to Park.”

SpotHero. “How SpotHero Works.”

PayByPhone. “Simplify Your Journey.”

## 4.2 Project Repository

The project repository stores the progressively updated project-management document and related project files.

GitHub repository: https://github.com/emenz-lab/CIS-Smart-Parking-Platform

# Homework 2 Work Breakdown Structure and Timeline

Homework 2 converts the approved parking-platform scope into assignable work packages and a coordinated semester schedule. The WBS and timeline use the same deliverables so scope, ownership, dependencies, and timing remain consistent.

# 5. Work Breakdown Structure

Level 1 represents the full project, Level 2 identifies major deliverables, and Level 3 defines assignable work packages. Selected Level 3 packages include Level 4 tasks to clarify the work further.

| WBS ID | Deliverable or Work Package | Level | Primary Owner |
| --- | --- | --- | --- |
| 1.0 | Smart Parking Platform | Entire Project | Project Manager |
| 1.1 | Project Planning and Requirements | Level 2 Deliverable | Project Manager |
| 1.1.1 | Stakeholder and user analysis | Level 3 Work Package | Project Manager |
| 1.1.2 | Requirements elicitation and validation | Level 3 Work Package | Project Manager / All Teams |
| 1.1.3 | Competitive analysis of parking solutions | Level 3 Work Package | Business Analyst |
| 1.1.4 | Scope, risk, and compliance plan | Level 3 Work Package | Project Manager |
| 1.2 | System and Experience Design | Level 2 Deliverable | Architecture / UX |
| 1.2.1 | System architecture and database design | Level 3 Work Package | Backend/API Team |
| 1.2.2 | Mobile and web interface prototypes | Level 3 Work Package | Mobile / Web Teams |
| 1.2.3 | Security, privacy, and access design | Level 3 Work Package | Backend/API Team |
| 1.3 | Core Platform Development | Level 2 Deliverable | Development Teams |
| 1.3.1 | Identity and account services | Level 3 Work Package | Backend/API Team |
| 1.3.1.1 | Registration, login, and session management | Level 4 Task | Backend/API Team |
| 1.3.1.2 | Driver, operator, and administrator roles | Level 4 Task | Backend/API Team |
| 1.3.2 | Parking inventory and availability services | Level 3 Work Package | Backend/API Team |
| 1.3.2.1 | Facility and parking-space records | Level 4 Task | Backend/API Team |
| 1.3.2.2 | Real-time occupancy status updates | Level 4 Task | Backend/API Team |
| 1.3.3 | Reservation services | Level 3 Work Package | Backend/API Team |
| 1.3.4 | Mobile driver application | Level 3 Work Package | Mobile Application Team |
| 1.3.5 | Web driver application | Level 3 Work Package | Web Application Team |
| 1.3.6 | Operator dashboard and administration | Level 3 Work Package | Web / Backend Teams |
| 1.3.7 | Reporting and occupancy analytics | Level 3 Work Package | Web / Backend Teams |
| 1.4 | External Integrations | Level 2 Deliverable | Integration Teams |
| 1.4.1 | Interactive map and location search | Level 3 Work Package | Mapping & Location Team |
| 1.4.2 | External navigation service integration | Level 3 Work Package | Mapping & Location Team |
| 1.4.3 | Digital payment processing | Level 3 Work Package | Payment Integration Team |
| 1.4.4 | Receipts and transaction history | Level 3 Work Package | Payment / Backend Teams |
| 1.4.5 | Notifications and alerts | Level 3 Work Package | Backend / Mobile Teams |
| 1.5 | Quality Assurance and Release | Level 2 Deliverable | QA & Testing Team |
| 1.5.1 | Test planning and test-case design | Level 3 Work Package | QA & Testing Team |
| 1.5.2 | Functional and integration testing | Level 3 Work Package | QA & Testing Team |
| 1.5.3 | Security, privacy, and performance testing | Level 3 Work Package | QA & Testing Team |
| 1.5.4 | User acceptance testing and defect fixes | Level 3 Work Package | QA / All Teams |
| 1.5.5 | Deployment, documentation, and handoff | Level 3 Work Package | Project Manager / All Teams |

Table 2. Work Breakdown Structure for the Smart Parking Platform.

# 6. Draft Project Timeline

The schedule uses overlapping work streams so specialized teams can work in parallel. Project management, stakeholder communication, risk monitoring, and status reporting continue throughout all 12 weeks.

| ID | Activity | Weeks | Owner | Depends On |
| --- | --- | --- | --- | --- |
| T1 | Initiation, stakeholder analysis, and competitive research | 1-2 | Project Manager | None |
| T2 | Requirements validation, scope, risk, and compliance plan | 1-3 | Project Manager / All Teams | T1 |
| T3 | Architecture, database, security, and UX design | 2-4 | Backend / Mobile / Web | T2 |
| T4 | Identity, account roles, and authentication services | 4-5 | Backend/API Team | T3 |
| T5 | Parking inventory, availability, and reservation services | 4-7 | Backend/API Team | T3 |
| T6 | Mobile driver application | 5-8 | Mobile Application Team | T3, T4 |
| T7 | Web driver application | 5-8 | Web Application Team | T3, T4 |
| T8 | Map, location search, and navigation integrations | 5-7 | Mapping & Location Team | T3, T5 |
| T9 | Payments, receipts, and transaction history | 6-8 | Payment / Backend Teams | T4, T5 |
| T10 | Operator dashboard, reporting, and analytics | 6-9 | Web / Backend Teams | T5 |
| T11 | Notifications and alerts | 7-9 | Backend / Mobile Teams | T4, T5 |
| T12 | QA planning and continuous feature testing | 3-9 | QA & Testing Team | T2 |
| T13 | System integration, security, privacy, and performance testing | 9-10 | QA & Testing Team | T6-T11 |
| T14 | User acceptance testing and defect resolution | 10-11 | QA / All Teams | T13 |
| T15 | Deployment preparation, documentation, and final handoff | 11-12 | Project Manager / All Teams | T14 |

Table 3. Draft timeline and task dependencies.

# 7. Gantt Chart

The chart schedules the same activities listed in Table 3. Orange represents planning, purple represents design, blue represents development and integration, green represents testing, and teal represents release work.

| ID | Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T1 | Initiation, stakeholder analysis, and competitive research | ● | ● |  |  |  |  |  |  |  |  |  |  |
| T2 | Requirements validation, scope, risk, and compliance plan | ● | ● | ● |  |  |  |  |  |  |  |  |  |
| T3 | Architecture, database, security, and UX design |  | ● | ● | ● |  |  |  |  |  |  |  |  |
| T4 | Identity, account roles, and authentication services |  |  |  | ● | ● |  |  |  |  |  |  |  |
| T5 | Parking inventory, availability, and reservation services |  |  |  | ● | ● | ● | ● |  |  |  |  |  |
| T6 | Mobile driver application |  |  |  |  | ● | ● | ● | ● |  |  |  |  |
| T7 | Web driver application |  |  |  |  | ● | ● | ● | ● |  |  |  |  |
| T8 | Map, location search, and navigation integrations |  |  |  |  | ● | ● | ● |  |  |  |  |  |
| T9 | Payments, receipts, and transaction history |  |  |  |  |  | ● | ● | ● |  |  |  |  |
| T10 | Operator dashboard, reporting, and analytics |  |  |  |  |  | ● | ● | ● | ● |  |  |  |
| T11 | Notifications and alerts |  |  |  |  |  |  | ● | ● | ● |  |  |  |
| T12 | QA planning and continuous feature testing |  |  | ● | ● | ● | ● | ● | ● | ● |  |  |  |
| T13 | System integration, security, privacy, and performance testing |  |  |  |  |  |  |  |  | ● | ● |  |  |
| T14 | User acceptance testing and defect resolution |  |  |  |  |  |  |  |  |  | ● | ● |  |
| T15 | Deployment preparation, documentation, and final handoff |  |  |  |  |  |  |  |  |  |  | ● | ● |

Figure 1. Twelve-week Gantt chart for Smart Parking Platform delivery.

# 8. Milestones and Scheduling Notes

| Milestone | Exit Condition |
| --- | --- |
| End of Week 2 | Stakeholders identified and competitive research completed. |
| End of Week 3 | Requirements baseline, initial scope, risks, and compliance needs approved. |
| End of Week 4 | Architecture, data model, security approach, and interface prototypes approved. |
| End of Week 8 | Driver applications and major external integrations are feature-complete. |
| End of Week 9 | Operator dashboard, analytics, and notification functions are feature-complete. |
| End of Week 10 | Integrated system passes security, privacy, and performance testing. |
| End of Week 11 | User acceptance testing is complete and critical defects are resolved. |
| End of Week 12 | Release candidate, documentation, and final handoff are complete. |

## Scheduling Notes

Backend services begin before most user-facing development because the mobile and web applications depend on shared account, parking, and reservation APIs.

Mapping and payment integrations are scheduled early enough to correct third-party service problems before final testing.

QA starts during Week 3 and continues alongside development instead of waiting until all features are complete.

Weeks 10 and 11 focus on user acceptance testing and defect correction before the Week 12 release.

Project management, team coordination, risk tracking, and stakeholder communication continue throughout the schedule.

## WBS to Schedule Traceability

The schedule covers each Level 2 WBS deliverable: Planning and Requirements (T1-T2), System and Experience Design (T3), Core Platform Development (T4-T7 and T10), External Integrations (T8-T9 and T11), and Quality Assurance and Release (T12-T15).

# Homework 3– Product Backlog and Sprint 1 Planning

Description: For the Smart Parking Platform project, I created a product backlog containing 45 total backlog items. The backlog includes 5 login items, 15 user/operator UI items, 15 backend process items, and 10 reporting items. After creating the product backlog, I selected 15 high-priority items for Sprint 1. Sprint 1 focuses on establishing the basic foundation of the platform, including user and operator login, role-based access, the driver interface, parking availability features, and the backend processes needed to support them. The remaining 30 items will stay in the Product Backlog for future sprints.